## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: none principals in environment 'test'
Project ID | PRJ-9201
Project name | PRACTICE TEST - Sample residential building (third-party sample BOQ)
Customer | NONE - practice exercise
Document ID | PRJ-9201-D42
Title | Open actions and outstanding information register
Revision | 1
Issue date | 2026-10-14
Status | BLOCKED
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v1
Estimate fingerprint | 400c9f6df7ae5579
Template | T-OPEN-ACTIONS@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Outstanding
Ref | Item | Status | Owner
TQ-PRJ-9201-001 | Resolve query (technical): BOQ item 1.1 ('Excavation in pits for footings') uses open wording (assumed, assumption, confirm, not printed) in: Remar | Draft | Estimator
TQ-PRJ-9201-002 | Resolve query (technical): BOQ item 7.1 ('Roof and canopy members') uses open wording (not stated) in: Section. Please state the exact scope, exten | Draft | Estimator
TQ-PRJ-9201-003 | Resolve query (boq_discrepancy): BOQ items 5.2 and 5.3 are almost identical ('Door 800 × 2400 mm' vs 'Door 802 × 2400 mm'; sizes differ by <= 1%). Are th | Draft | Estimator
TQ-PRJ-9201-004 | Resolve query (boq_discrepancy): BOQ items 5.16 and 5.20 are almost identical ('Window 1206 × 2000 mm' vs 'Window 1200 × 2000 mm'; sizes differ by <= 1%) | Draft | Estimator
TQ-PRJ-9201-005 | Resolve query (missing_input): Document ITT-CONTRACT (Invitation to tender, conditions of contract, BOQ preamble / method of measurement (NOT provided) | Draft | Estimator
TQ-PRJ-9201-006 | Resolve query (missing_input): Document DWG-ARCH-SET (Architect's drawing set - 'a 16-sheet drawing set' (p.1): ground-floor plan, first-floor plan, ro | Draft | Estimator
TQ-PRJ-9201-007 | Resolve query (missing_input): Document DWG-MEP (Mechanical, plumbing, electrical, fire, ELV drawings (NOT provided; not in scope of the source BOQ)) i | Draft | Estimator
TQ-PRJ-9201-008 | Resolve query (missing_input): Document DWG-STR-COLUMN (Structural column keys and column details (items 2.2-2.4; NOT provided)) is required for the te | Draft | Estimator
TQ-PRJ-9201-009 | Resolve query (missing_input): Document DWG-STR-FOOTING (Structural footing layout (basis of item 2.1; NOT provided)) is required for the tender but ha | Draft | Estimator
TQ-PRJ-9201-010 | Resolve query (missing_input): Document DWG-STR-SLABBEAM (Structural slab/beam sheets and beam details (items 2.5-2.9; NOT provided)) is required for t | Draft | Estimator
TQ-PRJ-9201-011 | Resolve query (missing_input): Document DWG-STR-STAIR (Structural stair sheet - the source says it was 'quarantined' (item 2.10; NOT provided)) is requ | Draft | Estimator
TQ-PRJ-9201-012 | Resolve query (missing_input): Document BBS-REINF (Reinforcement bar bending schedule - the source says it is excluded (p.7; NOT provided)) is required | Draft | Estimator
TQ-PRJ-9201-013 | Resolve query (missing_input): Document SPEC-ARCH (Architectural specification: plaster, door and window schedules, railings (NOT provided)) is require | Draft | Estimator
TQ-PRJ-9201-014 | Resolve query (missing_input): Document SPEC-STRUCT (Structural / concrete / masonry specification (grades, cover, mix; NOT provided)) is required for | Draft | Estimator
TQ-PRJ-9201-015 | Resolve query (missing_input): Document DWG-SITE-LEVELS (Site survey / natural ground level (item 1.1 assumption; NOT provided)) is required for the te | Draft | Estimator
TQ-PRJ-9201-016 | Resolve query (assumption_confirmation): 11 mandatory assumption(s) in 'Commercial terms and payment' need confirmation of the project basis: ASMP-I-001 Commerci | Draft | Estimator
TQ-PRJ-9201-017 | Resolve query (assumption_confirmation): 6 mandatory assumption(s) in 'Commissioning, testing and handover' need confirmation of the project basis: ASMP-K-001 In | Draft | Estimator
TQ-PRJ-9201-018 | Resolve query (assumption_confirmation): 2 mandatory assumption(s) in 'Logistics, transport and landed cost' need confirmation of the project basis: ASMP-F-001 D | Draft | Estimator
TQ-PRJ-9201-019 | Resolve query (assumption_confirmation): 6 mandatory assumption(s) in 'Material, labour, plant and equipment rates' need confirmation of the project basis: ASMP- | Draft | Estimator
TQ-PRJ-9201-020 | Resolve query (assumption_confirmation): 8 mandatory assumption(s) in 'Preliminaries and indirects' need confirmation of the project basis: ASMP-H-001 Indirect c | Draft | Estimator
TQ-PRJ-9201-021 | Resolve query (assumption_confirmation): 9 mandatory assumption(s) in 'Productivity and workforce' need confirmation of the project basis: ASMP-D-001 Paid hours | Draft | Estimator
TQ-PRJ-9201-022 | Resolve query (assumption_confirmation): 9 mandatory assumption(s) in 'Quantities and measurement' need confirmation of the project basis: ASMP-B-001 Measurement | Draft | Estimator
TQ-PRJ-9201-023 | Resolve query (assumption_confirmation): 8 mandatory assumption(s) in 'Risk and contingency' need confirmation of the project basis: ASMP-L-001 Rate source confi | Draft | Estimator
TQ-PRJ-9201-024 | Resolve query (assumption_confirmation): 16 mandatory assumption(s) in 'Scope and design' need confirmation of the project basis: ASMP-A-001 Design stage of esti | Draft | Estimator
TQ-PRJ-9201-025 | Resolve query (assumption_confirmation): 10 mandatory assumption(s) in 'Taxes and statutory costs' need confirmation of the project basis: ASMP-J-001 Default tax | Draft | Estimator
TQ-PRJ-9201-026 | Resolve query (boq_discrepancy): Item 1.3 'Backfill around footings' (240.58 m3) is printed as 'excavation - footing - blinding'. 314.04 - 55.40 - 18.33 | Draft | Estimator
TQ-PRJ-9201-027 | Resolve query (boq_discrepancy): Page-2 totals differ from the sum of the item lines: RCC 129.42 vs 129.43, formwork 1,746.67 vs 1,746.68, masonry 111.38 | Draft | Estimator
TQ-PRJ-9201-028 | Resolve query (missing_input): Natural ground level is 'not printed - assumed at project +/-0.00'. Please supply the site survey / levels. Items 1.1, 1 | Draft | Estimator
TQ-PRJ-9201-029 | Resolve query (missing_input): The BOQ was measured from a '16-sheet drawing set' (and a 3D model of 434 elements). None of the sheets or the model wer | Draft | Estimator
TQ-PRJ-9201-030 | Resolve query (technical): Item 2.10 RC stairs (4.13 m3): the structural stair sheet is stated as 'quarantined' and the quantity was taken from arc | Draft | Estimator
TQ-PRJ-9201-031 | Resolve query (scope_exclusion): Reinforcement steel and its bar bending schedule are excluded from the BOQ. Is steel to be priced by the contractor from | Draft | Estimator
TQ-PRJ-9201-032 | Resolve query (scope_exclusion): Plaster (item 4.4) is measured gross, openings not deducted. Which method of measurement applies to the tender (the docu | Draft | Estimator
TQ-PRJ-9201-033 | Resolve query (scope_exclusion): Flooring, finishes, plumbing, electrical and other services are not in the BOQ ('those come with a full BOQ'). Please co | Draft | Estimator
TQ-PRJ-9201-034 | Resolve query (technical): Openings with unusual sizes: Door 6467x3140, Window 387x3140, Window 368x3140, Window 600x2950, Window 4274x2000. Please | Draft | Estimator
TQ-PRJ-9201-035 | Resolve query (boq_discrepancy): Door 900x2400 (7 nos), 800x2400 (4), 802x2400 (1), 736x2400 (1): 802 and 736 look like duplicates/variants of 800. Pleas | Draft | Estimator
TQ-PRJ-9201-036 | Resolve query (missing_input): No specification is supplied: concrete grade, cover and mix, masonry unit type and mortar, plaster thickness/mix, door a | Draft | Estimator
TQ-PRJ-9201-037 | Resolve query (technical): The source uses IS 1200 and INR. Which measurement standard, currency, region, tax and contractual basis apply to this e | Draft | Estimator
TQ-PRJ-9201-038 | Resolve query (design_interface): Item 7.1 'Roof and canopy members' (48.85 m) gives only a running length. Material (steel/RCC/timber), section, finish a | Draft | Estimator
TQ-PRJ-9201-039 | Resolve query (boq_discrepancy): The document says quantities were delivered 6 September 2026 and the page was published 1 October 2026; no revision iden | Draft | Estimator
TQ-PRJ-9201-040 | Resolve query (commercial): Rates, amounts and the abstract of cost are blank by design. Which rate basis (DSR, SOR, market) and currency is to be u | Draft | Estimator
ACT-PRJ-9201-001 | Obtain and register the 16-sheet architectural + structural drawing set; then a person verifies every BOQ quantity against it (0 of 48 lines are verifiable today) | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-002 | MANUAL TAKEOFF REQUIRED: reinforcement steel (kg) and bar bending schedule - excluded from the source BOQ | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-003 | MANUAL TAKEOFF REQUIRED: plaster net area after deducting openings per the method of measurement the customer names | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-004 | MANUAL TAKEOFF REQUIRED: flooring, wall/ceiling finishes, waterproofing, painting, joinery | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-005 | MANUAL TAKEOFF REQUIRED: plumbing, drainage, electrical, HVAC, fire and ELV quantities | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-006 | MANUAL TAKEOFF REQUIRED: external works, boundary wall, gate, site drainage, utilities connections | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-007 | MANUAL TAKEOFF REQUIRED: structural stair - source says the structural stair sheet was quarantined; stair concrete (4.13 m3) was taken from architectural plans | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-008 | Confirm natural ground level; re-measure excavation 1.1, blinding 1.2, backfill 1.3 together if it changes | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-009 | MANUAL TAKEOFF REQUIRED: roof and canopy member sections/material/weights (only a run length is given) | Open (due None) | UNASSIGNED (estimator to assign)
ACT-PRJ-9201-010 | MANUAL TAKEOFF REQUIRED: railing type/height/material and fixings (only a run length is given) | Open (due None) | UNASSIGNED (estimator to assign)
GATE | the project is flagged as a demonstration project | Open | Commercial Approver
GATE | the environment is 'test', not 'production' | Open | Commercial Approver
GATE | project region/currency (KSA-ALL / SAR) are system defaults, not confirmed by a person | Open | Commercial Approver
GATE | estimate approval: no approval record | Open | Commercial Approver
GATE | letter of offer: none generated | Open | Commercial Approver
GATE | tender-export approval: no approval record | Open | Commercial Approver
GATE | reconciliation gate blocked by 50 finding(s) | Open | Commercial Approver
GATE | estimate state is 'Preliminary — Incomplete' | Open | Commercial Approver
GATE | 40 unresolved material technical/commercial queries: TQ-PRJ-9201-001, TQ-PRJ-9201-002, TQ-PRJ-9201-003, TQ-PRJ-9201-004, TQ-PRJ-9201-005, TQ-PRJ-9201-006 | Open | Commercial Approver
GATE | required tender document(s) not received: ITT-CONTRACT, DWG-ARCH-SET, DWG-MEP, DWG-STR-COLUMN, DWG-STR-FOOTING, DWG-STR-SLABBEAM, DWG-STR-STAIR, BBS-REINF, SPEC-ARCH, SPEC-STRUCT, DWG-SITE-LEVELS | Open | Commercial Approver