## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
HYPOTHETICAL POST-AWARD HANDOVER - SIMULATION ONLY - NO AWARD HAS BEEN MADE ¦ DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-H12
Title | Commercial terms, payment milestones and retention
Revision | 1
Issue date | 2027-02-15
Status | Preliminary (SIMULATED HANDOVER)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | H-COMMERCIAL@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Offer
Item | Value
Net price (SAR, before VAT) | 4,206,332.22
VAT (SAR) | 630,948.10
Final payable (SAR) | 4,837,268.79
Estimate state | Complete
Letter of offer | v1 (Approved)

## Commercial trace
Step | Amount | Formula
Pre-contingency cost (C0) | 3744953.9 | Direct + Indirect
Contingency | 149798.16 | 4% x base[direct_indirect]
Total cost (T) | 3894752.06 | C0 + contingency + risk + escalation
Selling price (markup) | 4206332.22 | T x (1 + 8%)
Tax VAT-STD | 630949.83 | 15% x 4206332.22

## Cash flow - summary
Field | Value
price | 4206332.22
total_cost | 3452410.00
retention_total | 210316.61
advance | 420633.22
interest_total | 11043.72
peak_funding | 1042833.82
peak_funding_month | 9
performance_bond_cost | 12093.21
bond_months | 23.00
final_balance | 450334.60
terms | {"code": "PAY-CLOSURE", "version": 1, "name": "SYNTHETIC payment terms (from the synthetic customer response)", "advance_pct": "10.00", "retention_pct": "5.00", "retention_release_at_completion_pct": "50.00", "defects_months": "12.00", "certification_lag_months": "1.00", "payment_lag_months": "1....
assumptions | ["Value earned in a month is proportional to cost incurred in that month (margin is not front- or back-loaded).", "Amounts exclude VAT.", "Interest accrues monthly on a negative opening balance and is capitalised; positive balances earn nothing.", "The advance is received in the first month and r...
project_id | PRJ-9101
first_month | 2027-03
unscheduled_cost | 0.00
allocated_by_rule | {"TA-SUP": "210000.00", "TA-TEMP": "36000.00", "TA-HSE": "18000.00", "TA-BACKFILL": "33280.00", "TA-ANCHOR": "31800.00", "TA-PLANT": "130700.00", "TA-FIRE": "79100.00", "TA-ELV": "67200.00"}
complete | True
status | COMPLETE
estimate_state | Complete
reconciliation | {"net_price": "4206332.22", "valued_price": "4206332.22", "unallocated_price_share": "0.00", "direct_cost": "3452410.00", "allocated_direct_cost": "3452410.00", "unallocated_direct_cost": "0.00", "indirect_cost": "292543.90", "indirect_cash_factor": "1.08", "cash_out_total": "3744953.90", "cash_i...
note | Analysis only. Conventions: indirects are paid with the direct cost they follow; contingency/risk/margin are not cash-out; only allocated cost is valued. Financing and bond cost may be proposed as Draft indirect items (refused while incomplete).

## Cash flow - valuations
month | value | advance_recovery | retention | net_certified
0 | 230771.59 | 23077.16 | 11538.58 | 196155.85
1 | 155798.38 | 15579.84 | 7789.92 | 132428.62
2 | 477813.57 | 47781.36 | 23890.68 | 406141.54
3 | 892878.91 | 89287.89 | 44643.95 | 758947.07
4 | 351865.04 | 35186.50 | 17593.25 | 299085.28
5 | 55216.73 | 5521.67 | 2760.84 | 46934.22
6 | 36370.47 | 3637.05 | 1818.52 | 30914.90
7 | 280566.25 | 28056.63 | 14028.31 | 238481.31
8 | 1527794.31 | 152779.43 | 76389.72 | 1298625.16
9 | 46005.86 | 4600.59 | 2300.29 | 39104.98
10 | 151251.11 | 15125.11 | 7562.56 | 128563.44

## Monthly cash position
month | cash_in | cash_out | net | interest | balance
0 | 420633.22 | 0.00 | 420633.22 | 0.00 | 420633.22
1 | 0.00 | 205459.04 | -205459.04 | 0.00 | 215174.18
2 | 196155.85 | 138709.38 | 57446.47 | 0.00 | 272620.65
3 | 132428.62 | 425403.82 | -292975.20 | 0.00 | -20354.55
4 | 406141.54 | 794942.05 | -388800.51 | 152.66 | -409307.72
5 | 758947.07 | 313270.15 | 445676.92 | 3069.81 | 33299.39
6 | 299085.28 | 49160.19 | 249925.09 | 0.00 | 283224.48
7 | 46934.22 | 32381.11 | 14553.11 | 0.00 | 297777.59
8 | 30914.90 | 249791.89 | -218877.00 | 0.00 | 78900.59
9 | 238481.31 | 1360215.73 | -1121734.42 | 0.00 | -1042833.82
10 | 1298625.16 | 40959.64 | 1257665.53 | 7821.25 | 207010.45
11 | 39104.98 | 134660.89 | -95555.90 | 0.00 | 111454.54
12 | 233721.75 | 0.00 | 233721.75 | 0.00 | 345176.29
13 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
14 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
15 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
16 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
17 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
18 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
19 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
20 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
21 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
22 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29
23 | 105158.31 | 0.00 | 105158.31 | 0.00 | 450334.60