## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
HYPOTHETICAL POST-AWARD HANDOVER - SIMULATION ONLY - NO AWARD HAS BEEN MADE ¦ DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-H14
Title | Outstanding decisions and actions
Revision | 1
Issue date | 2027-02-15
Status | Preliminary (SIMULATED HANDOVER)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | H-OPEN@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Outstanding
Ref | Item | Status | Owner
ACT-PRJ-9101-001 | Place the pump skid purchase order (order date per the long-lead item) | Open (due 2027-02-21) | SIMULATED OWNER - Procurement Manager (test)
ACT-PRJ-9101-002 | Submit the baseline programme to the customer | Open (due 2027-03-21) | SIMULATED OWNER - Planning Engineer (test)
ACT-PRJ-9101-003 | Issue method statements and ITPs for hot work and excavation | Open (due 2027-03-28) | SIMULATED OWNER - Project Manager (test)
GATE | the project is flagged as a demonstration project | Open | Commercial Approver
GATE | synthetic data is used in the estimate | Open | Commercial Approver
GATE | the environment is 'test', not 'production' | Open | Commercial Approver
GATE | estimate approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | estimate approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | estimate approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | offer approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | offer approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | offer approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | tender-export approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | tender-export approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | tender-export approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | rate 928: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 928: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 928: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 929: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 929: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 929: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 930: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 930: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 930: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 931: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 931: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 931: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 932: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 932: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 932: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 933: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 933: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 933: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 934: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 934: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 934: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 935: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 935: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 935: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 936: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 936: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 936: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 937: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 937: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 937: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 938: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 938: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 938: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 939: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 939: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 939: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 940: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 940: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 940: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 941: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 941: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 941: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 942: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 942: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 942: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 943: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 943: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 943: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 944: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 944: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 944: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 945: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 945: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 945: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 946: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 946: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 946: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 947: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 947: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 947: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 948: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 948: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 948: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 949: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 949: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 949: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 950: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 950: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 950: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 951: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 951: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 951: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 952: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 952: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 952: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 953: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 953: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 953: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 954: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 954: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 954: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 955: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 955: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 955: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 956: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 956: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 956: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 957: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 957: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 957: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 958: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 958: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 958: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 959: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 959: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 959: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 960: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 960: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 960: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 961: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 961: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 961: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 962: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 962: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 962: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 963: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 963: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 963: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 964: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 964: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 964: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 965: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 965: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 965: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 966: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 966: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 966: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 967: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 967: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 967: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 968: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 968: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 968: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 969: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 969: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 969: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | rate 970: approved by a 'test' principal (test-procurement); only registered human users count | Open | Commercial Approver
GATE | rate 970: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | rate 970: test-procurement is not (or is no longer) an active registered human user holding role 'Procurement Reviewer' | Open | Commercial Approver
GATE | commercial policy approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | commercial policy approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | commercial policy approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | tax category VAT-STD approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | tax category VAT-STD approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | tax category VAT-STD approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | indirect IND-HO: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | indirect IND-HO: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | indirect IND-HO: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | indirect IND-INS: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | indirect IND-INS: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | indirect IND-INS: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | indirect IND-SITE: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | indirect IND-SITE: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | indirect IND-SITE: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | reconciliation exception PLANT_HIRE_DAYS (SYN-C-050): accepted by a 'test' principal; recorded in environment 'test' | Open | Commercial Approver
GATE | programme baseline rests on synthetic or provisional norms / profile / calendar | Open | Commercial Approver
GATE | productivity norm N-BACK: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-BACK: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-BACK: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-CABLE: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-CABLE: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-CABLE: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-COAT: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-COAT: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-COAT: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-FIBRE: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-FIBRE: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-FIBRE: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-EXC: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-EXC: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-EXC: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-EXCH: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-EXCH: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-EXCH: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-FORM: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-FORM: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-FORM: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-NDT: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-NDT: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-NDT: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-PIPE: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-PIPE: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-PIPE: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-POUR: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-POUR: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-POUR: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-PUMP: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-PUMP: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-PUMP: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-REBAR: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-REBAR: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-REBAR: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-ROAD: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-ROAD: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-ROAD: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-SHORE: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-SHORE: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-SHORE: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-STEEL: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-STEEL: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-STEEL: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-SUPP: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-SUPP: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-SUPP: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-TRAY: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-TRAY: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-TRAY: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | productivity norm N-WELD: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | productivity norm N-WELD: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | productivity norm N-WELD: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | programme baseline v2: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | programme baseline v2: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | programme baseline v2: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | workforce profile WP-MID: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | workforce profile WP-MID: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | workforce profile WP-MID: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | document PRJ-9101-D16 approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | document PRJ-9101-D16 approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | document PRJ-9101-D16 approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver
GATE | document PRJ-9101-D06 approval: approved by a 'test' principal (test-commercial); only registered human users count | Open | Commercial Approver
GATE | document PRJ-9101-D06 approval: recorded in environment 'test', not 'production' | Open | Commercial Approver
GATE | document PRJ-9101-D06 approval: test-commercial is not (or is no longer) an active registered human user holding role 'Commercial Approver' | Open | Commercial Approver

## Required-inputs checklist
Key | input | needed_for | status_note | Status
drawings | Complete drawing set with all revisions | quantities and methodology | DWG-EL-010 missing at enquiry | Draft
payment | Payment, retention and bond terms | cash-flow basis and financing | not stated in the ITT | Draft
quality | Customer quality-plan requirement | documents D27, D28, D30 | conflicting statements | Draft
site | Site access and working-hour rules | calendar and programme | to be confirmed | Draft

## Responsibility assignment
Key | role | responsibility | assigned_to | Status
estimating | Estimating lead | BOQ mapping, pricing, queries | SIMULATED OWNER - Lead Estimator (test) | Draft
commercial | Commercial approver | commercial policy, offer, final gate | SIMULATED OWNER - Commercial Manager (test) | Draft
procurement | Procurement lead | RFQs, quote levelling, long-lead items | SIMULATED OWNER - Procurement Manager (test) | Draft