## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-D10
Title | Commercial clarifications
Revision | 2
Issue date | 2027-02-15
Status | Preliminary (DEMONSTRATION)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | T-COMM-CLARIF@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Commercial clarifications
Query ID | Register | Question | Why | Due | Status | Response | Cost impact (SAR) | Time impact (d)
TQ-PRJ-9101-029 | commercial | Please confirm the advance payment, retention percentage and retention release terms applicable to this contract. | Payment terms drive the cash-flow basis (document D13) and financing cost. | 2027-02-22 | Closed | SYNTHETIC CUSTOMER RESPONSE: advance 10%, retention 5% (50% released at completion, balance after a 12-month defects period), payment 1 month after certification; performance bond 10%. [SYNTHETIC RESPONSE]