## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-D11
Title | Risk and opportunity register
Revision | 2
Issue date | 2027-02-15
Status | Preliminary (DEMONSTRATION)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | T-RISK@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Risks
ID | Title | Category | Probability % | Cost low | Likely | High | Status
RSK-PRJ-9101-001 | Ground conditions in hard material | Technical | 30 | 20000 | 60000 | 150000 | Open
RSK-PRJ-9101-002 | Pump skid delivery delay | Technical | 25 | 0 | 45000 | 120000 | Open
RSK-PRJ-9101-003 | Interface with existing fire ring main | Technical | 20 | 10000 | 30000 | 90000 | Open