# Payment milestones and cash-flow basis

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D13 |
| Title | Payment milestones and cash-flow basis |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-CASHFLOW@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Cash flow - summary

| Field | Value |
| --- | --- |
| price | 4206332.22 |
| total_cost | 3452410.00 |
| retention_total | 210316.61 |
| advance | 420633.22 |
| interest_total | 11043.72 |
| peak_funding | 1042833.82 |
| peak_funding_month | 9 |
| performance_bond_cost | 12093.21 |
| bond_months | 23.00 |
| final_balance | 450334.60 |
| terms | {"code": "PAY-CLOSURE", "version": 1, "name": "SYNTHETIC payment terms (from the synthetic customer response)", "advance_pct": "10.00", "retention_pct": "5.00", "retention_release_at_completion_pct": "50.00", "defects_months": "12.00", "certification_lag_months": "1.00", "payment_lag_months": "1.... |
| assumptions | ["Value earned in a month is proportional to cost incurred in that month (margin is not front- or back-loaded).", "Amounts exclude VAT.", "Interest accrues monthly on a negative opening balance and is capitalised; positive balances earn nothing.", "The advance is received in the first month and r... |
| project_id | PRJ-9101 |
| first_month | 2027-03 |
| unscheduled_cost | 0.00 |
| allocated_by_rule | {"TA-SUP": "210000.00", "TA-TEMP": "36000.00", "TA-HSE": "18000.00", "TA-BACKFILL": "33280.00", "TA-ANCHOR": "31800.00", "TA-PLANT": "130700.00", "TA-FIRE": "79100.00", "TA-ELV": "67200.00"} |
| complete | True |
| status | COMPLETE |
| estimate_state | Complete |
| reconciliation | {"net_price": "4206332.22", "valued_price": "4206332.22", "unallocated_price_share": "0.00", "direct_cost": "3452410.00", "allocated_direct_cost": "3452410.00", "unallocated_direct_cost": "0.00", "indirect_cost": "292543.90", "indirect_cash_factor": "1.08", "cash_out_total": "3744953.90", "cash_i... |
| note | Analysis only. Conventions: indirects are paid with the direct cost they follow; contingency/risk/margin are not cash-out; only allocated cost is valued. Financing and bond cost may be proposed as Draft indirect items (refused while incomplete). |

# Cash flow - valuations

| month | value | advance_recovery | retention | net_certified |
| --- | --- | --- | --- | --- |
| 0 | 230771.59 | 23077.16 | 11538.58 | 196155.85 |
| 1 | 155798.38 | 15579.84 | 7789.92 | 132428.62 |
| 2 | 477813.57 | 47781.36 | 23890.68 | 406141.54 |
| 3 | 892878.91 | 89287.89 | 44643.95 | 758947.07 |
| 4 | 351865.04 | 35186.50 | 17593.25 | 299085.28 |
| 5 | 55216.73 | 5521.67 | 2760.84 | 46934.22 |
| 6 | 36370.47 | 3637.05 | 1818.52 | 30914.90 |
| 7 | 280566.25 | 28056.63 | 14028.31 | 238481.31 |
| 8 | 1527794.31 | 152779.43 | 76389.72 | 1298625.16 |
| 9 | 46005.86 | 4600.59 | 2300.29 | 39104.98 |
| 10 | 151251.11 | 15125.11 | 7562.56 | 128563.44 |

# Monthly cash position

| month | cash_in | cash_out | net | interest | balance |
| --- | --- | --- | --- | --- | --- |
| 0 | 420633.22 | 0.00 | 420633.22 | 0.00 | 420633.22 |
| 1 | 0.00 | 205459.04 | -205459.04 | 0.00 | 215174.18 |
| 2 | 196155.85 | 138709.38 | 57446.47 | 0.00 | 272620.65 |
| 3 | 132428.62 | 425403.82 | -292975.20 | 0.00 | -20354.55 |
| 4 | 406141.54 | 794942.05 | -388800.51 | 152.66 | -409307.72 |
| 5 | 758947.07 | 313270.15 | 445676.92 | 3069.81 | 33299.39 |
| 6 | 299085.28 | 49160.19 | 249925.09 | 0.00 | 283224.48 |
| 7 | 46934.22 | 32381.11 | 14553.11 | 0.00 | 297777.59 |
| 8 | 30914.90 | 249791.89 | -218877.00 | 0.00 | 78900.59 |
| 9 | 238481.31 | 1360215.73 | -1121734.42 | 0.00 | -1042833.82 |
| 10 | 1298625.16 | 40959.64 | 1257665.53 | 7821.25 | 207010.45 |
| 11 | 39104.98 | 134660.89 | -95555.90 | 0.00 | 111454.54 |
| 12 | 233721.75 | 0.00 | 233721.75 | 0.00 | 345176.29 |
| 13 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 14 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 15 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 16 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 17 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 18 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 19 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 20 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 21 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 22 | 0.00 | 0.00 | 0.00 | 0.00 | 345176.29 |
| 23 | 105158.31 | 0.00 | 105158.31 | 0.00 | 450334.60 |

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Cash-flow values use the current approved payment terms and programme; they are not part of the frozen estimate snapshot.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)