# Execution methodology

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D18 |
| Title | Execution methodology |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-METHODOLOGY@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Execution and constructability review

| Key | topic | content | Status |
| --- | --- | --- | --- |
| wbs | Wbs | Work breakdown: 23 activities grouped by BOQ trade (civil, structural, piping, mechanical, electrical, ELV, commissioning). | Draft |
| sequence | Sequence | Execution sequence follows the programme dependencies: mobilisation, excavation, pipe-rack foundations, steel, support fabrication, piping, welding, NDT, hydrotest, backfill/coating, E&I, commissioning, demobilisation. | Draft |
| work_fronts | Work Fronts | Work fronts per activity are limited to the values entered on the activities (maximum 3). | Draft |
| plant | Plant | One mobile crane serves steel erection and pump-skid setting; a telehandler serves pipe installation (hire terms in the plant exposure report). | Draft |
| workforce | Workforce | Selected profile Mid-sized crew (SYNTHETIC): peak direct manpower 18. | Draft |
| procurement | Procurement | Pump skids are a long-lead item; procurement-constrained dates are shown in the programme. | Draft |
| inspection | Inspection | Hold points follow the ITP register; NDT sample size is subject to the compliance deviation D-1. | Draft |
| interfaces | Interfaces | The fire-water tie-in is an interface with the existing ring main owned by the customer. | Draft |
| risks | Risks | Programme risks: hard-material excavation, pump skid delay, tie-in isolation windows (see the risk register). | Draft |
| temporary_works | Temporary Works | Temporary works: trench shoring (BOQ C-012) and scaffolding access hire (BOQ C-052); design of temporary works is by a competent engineer (not generated here). | Draft |
| access | Access | Access and working windows follow the project calendar (shutdown and reduced-hour windows are shown in D19); the customer's site access rules are a recorded required input. | Draft |
| testing_commissioning | Testing Commissioning | Hydrotest and flushing are a fixed 8-day activity, commissioning a fixed 10-day activity after coating, cable and fibre completion. | Draft |
| hse_interfaces | Hse Interfaces | HSE interfaces: hot-work and excavation permits (permit register), tie-in isolation with the existing ring main (interface register). | Draft |
| constraints | Constraints | Constraints and exclusions: see D09; unverified norms and the synthetic basis are listed in D37. | Draft |

# Execution sequence (work activities)

| Activity | Name | Predecessors | Crews | Work fronts | Norm |
| --- | --- | --- | --- | --- | --- |
| A-MOB | Mobilisation |  | 1 | 1 |  |
| A-EXC | Trench excavation | A-MOB | 2 | 2 | N-EXC |
| A-EXCH | Hard-material excavation | A-EXC | 1 | 1 | N-EXCH |
| A-SHORE | Trench shoring | A-MOB | 1 | 1 | N-SHORE |
| A-FORM | Pipe-rack formwork | A-EXC | 2 | 2 | N-FORM |
| A-REBAR | Pipe-rack reinforcement | A-EXC | 2 | 2 | N-REBAR |
| A-POUR | Pipe-rack concrete | A-FORM,A-REBAR | 1 | 1 | N-POUR |
| A-STEEL | Pipe-rack steel erection | A-POUR | 2 | 2 | N-STEEL |
| A-SUPP | Pipe support fabrication | A-POUR | 1 | 1 | N-SUPP |
| A-PUMP | Pump skid setting | A-POUR | 1 | 1 | N-PUMP |
| A-PIPE100 | Pipe installation DN100 | A-STEEL,A-SUPP | 3 | 3 | N-PIPE |
| A-PIPE50 | Pipe installation DN50 | A-STEEL,A-SUPP | 2 | 2 | N-PIPE |
| A-WELD | Butt welding | A-PIPE100,A-PIPE50 | 3 | 3 | N-WELD |
| A-NDT | Weld radiography | A-WELD | 1 | 1 | N-NDT |
| A-HYDRO | Hydrotest and flushing | A-NDT,A-PUMP | 1 | 1 |  |
| A-BACK | Backfill | A-HYDRO | 1 | 1 | N-BACK |
| A-ROAD | Road reinstatement | A-BACK | 1 | 1 | N-ROAD |
| A-COAT | Coating | A-HYDRO | 1 | 1 | N-COAT |
| A-TRAY | Cable tray | A-STEEL | 1 | 1 | N-TRAY |
| A-CABLE | Cable pulling | A-TRAY | 1 | 1 | N-CABLE |
| A-ELV | Fibre backbone | A-TRAY | 1 | 1 | N-FIBRE |
| A-COMM | Testing and commissioning | A-COAT,A-CABLE,A-ELV,A-ROAD | 1 | 1 |  |
| A-DEMOB | Demobilisation | A-COMM | 1 | 1 |  |

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Methodology topics are entered and reviewed by a competent person; none is generated as engineering advice.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)