# Construction programme and milestones

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D19 |
| Title | Construction programme and milestones |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-PROGRAMME@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Programme summary

| Item | Value |
| --- | --- |
| Baseline | v2 (Approved) |
| Workforce profile | Mid-sized crew (SYNTHETIC) (mid) |
| Unconstrained duration (working days) | 37 |
| Dependency-constrained | 196 |
| Procurement-constrained | 196 |
| Resource-constrained (baseline) | 231 |
| Calendar days | 327 |
| Start | 2027-03-07 |
| Finish | 2028-01-27 |
| Critical path | A-MOB > A-EXC > A-FORM > A-POUR > A-SUPP > A-PIPE100 > A-WELD > A-NDT > A-HYDRO > A-COAT > A-COMM > A-DEMOB |
| Claim | PROVISIONAL - NOT FOR RELIANCE: synthetic test inputs |

# Work calendar used (never assumed)

| Item | Value |
| --- | --- |
| Start date | 2027-03-07 |
| Working weekdays (0=Mon) | [0, 1, 2, 3, 6] |
| Standard hours per day | 8 |
| Reduced-hour windows | [{"frm": "2027-04-04", "to": "2027-04-29", "hours": "6"}] |
| Shutdowns | [{"frm": "2027-05-16", "to": "2027-05-18"}] |
| Holidays | ["2027-03-30"] |
| Calendar confirmed | True |

# Activities (working-day indices from project start)

| Code | Activity | Status | Labour hours | Unconstrained wd | Start | Finish | Resource delay | Float | Critical | Constraint |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A-MOB | Mobilisation | OK | 0.00 | 5 | 0 | 0 | 0 | 0 | CRITICAL |  |
| A-EXC | Trench excavation | OK | 255.00 | 8 | 0 | 15 | 0 | 0 | CRITICAL | resource-limited |
| A-EXCH | Hard-material excavation | OK | 180.00 | 10 | 43 | 53 | 30 | 173 |  | resource-limited |
| A-SHORE | Trench shoring | OK | 240.00 | 10 | 0 | 10 | 0 | 181 |  |  |
| A-FORM | Pipe-rack formwork | OK | 615.00 | 11 | 15 | 28 | 2 | 0 | CRITICAL |  |
| A-REBAR | Pipe-rack reinforcement | OK | 460.00 | 8 | 28 | 39 | 15 | 3 |  | resource-limited |
| A-POUR | Pipe-rack concrete | OK | 192.00 | 11 | 39 | 50 | 15 | 0 | CRITICAL |  |
| A-STEEL | Pipe-rack steel erection | OK | 403.20 | 6 | 53 | 65 | 18 | 7 |  | resource-limited |
| A-SUPP | Pipe support fabrication | OK | 230.40 | 13 | 50 | 63 | 15 | 0 | CRITICAL |  |
| A-PUMP | Pump skid setting | OK | 96.00 | 4 | 155 | 159 | 69 | 53 |  | resource-limited |
| A-PIPE100 | Pipe installation DN100 | OK | 2600.00 | 37 | 65 | 102 | 17 | 0 | CRITICAL |  |
| A-PIPE50 | Pipe installation DN50 | OK | 775.00 | 17 | 102 | 119 | 54 | 20 |  | resource-limited |
| A-WELD | Butt welding | OK | 1920.00 | 36 | 119 | 155 | 34 | 0 | CRITICAL |  |
| A-NDT | Weld radiography | OK | 260.00 | 22 | 155 | 177 | 34 | 0 | CRITICAL |  |
| A-HYDRO | Hydrotest and flushing | OK | 0.00 | 8 | 177 | 185 | 34 | 0 | CRITICAL |  |
| A-BACK | Backfill | OK | 144.00 | 8 | 185 | 193 | 34 | 20 |  |  |
| A-ROAD | Road reinstatement | OK | 120.00 | 4 | 217 | 221 | 58 | 20 |  | resource-limited |
| A-COAT | Coating | OK | 760.00 | 32 | 185 | 217 | 34 | 0 | CRITICAL |  |
| A-TRAY | Cable tray | OK | 480.00 | 20 | 65 | 85 | 24 | 102 |  |  |
| A-CABLE | Cable pulling | OK | 480.00 | 20 | 85 | 105 | 24 | 102 |  |  |
| A-ELV | Fibre backbone | OK | 144.00 | 12 | 85 | 97 | 24 | 110 |  |  |
| A-COMM | Testing and commissioning | OK | 0.00 | 10 | 221 | 231 | 38 | 0 | CRITICAL |  |
| A-DEMOB | Demobilisation | OK | 0.00 | 3 | 231 | 231 | 35 | 0 | CRITICAL |  |

# Gaps affecting the programme

| Activity | Kind | Detail |
| --- | --- | --- |
| A-EXC | NORM_EVIDENCE_SYNTHETIC | norm N-EXC v1: evidence 'synthetic' |
| A-EXCH | NORM_EVIDENCE_SYNTHETIC | norm N-EXCH v1: evidence 'synthetic' |
| A-SHORE | NORM_EVIDENCE_SYNTHETIC | norm N-SHORE v1: evidence 'synthetic' |
| A-FORM | NORM_EVIDENCE_SYNTHETIC | norm N-FORM v1: evidence 'synthetic' |
| A-REBAR | NORM_EVIDENCE_SYNTHETIC | norm N-REBAR v1: evidence 'synthetic' |
| A-POUR | NORM_EVIDENCE_SYNTHETIC | norm N-POUR v1: evidence 'synthetic' |
| A-STEEL | NORM_EVIDENCE_SYNTHETIC | norm N-STEEL v1: evidence 'synthetic' |
| A-SUPP | NORM_EVIDENCE_SYNTHETIC | norm N-SUPP v1: evidence 'synthetic' |
| A-PUMP | NORM_EVIDENCE_SYNTHETIC | norm N-PUMP v1: evidence 'synthetic' |
| A-PIPE100 | NORM_EVIDENCE_SYNTHETIC | norm N-PIPE v1: evidence 'synthetic' |
| A-PIPE50 | NORM_EVIDENCE_SYNTHETIC | norm N-PIPE v1: evidence 'synthetic' |
| A-WELD | NORM_EVIDENCE_SYNTHETIC | norm N-WELD v1: evidence 'synthetic' |
| A-NDT | NORM_EVIDENCE_SYNTHETIC | norm N-NDT v1: evidence 'synthetic' |
| A-BACK | NORM_EVIDENCE_SYNTHETIC | norm N-BACK v1: evidence 'synthetic' |
| A-ROAD | NORM_EVIDENCE_SYNTHETIC | norm N-ROAD v1: evidence 'synthetic' |
| A-COAT | NORM_EVIDENCE_SYNTHETIC | norm N-COAT v1: evidence 'synthetic' |
| A-TRAY | NORM_EVIDENCE_SYNTHETIC | norm N-TRAY v1: evidence 'synthetic' |
| A-CABLE | NORM_EVIDENCE_SYNTHETIC | norm N-CABLE v1: evidence 'synthetic' |
| A-ELV | NORM_EVIDENCE_SYNTHETIC | norm N-FIBRE v1: evidence 'synthetic' |

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Durations come from productivity norms; any norm that is not Approved, or any synthetic norm, makes the programme provisional.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)