# Workforce and resource-loading plan

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D20 |
| Title | Workforce and resource-loading plan |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-WORKFORCE@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Selected workforce profile

| Item | Value |
| --- | --- |
| Profile | Mid-sized crew (SYNTHETIC) |
| Archetype (configurable planning band) | mid |
| Pool (role: head-count per shift) | {"eq:crane": 1, "labourer": 6, "operator": 2, "semi_skilled": 4, "skilled": 7, "sub:electrical": 6} |
| Indirect staff | {"engineer": 1, "foreman": 2, "hse": 1, "qc": 1} |
| Shifts | 1 |
| Productive hours per shift | 6 |
| Peak direct manpower | 18 |
| Total labour-hours | 10354.60 |

# Daily direct manpower (working-day index: workers)

| Day | Workers |
| --- | --- |
| 0 | 7 |
| 1 | 7 |
| 2 | 7 |
| 3 | 7 |
| 4 | 7 |
| 5 | 7 |
| 6 | 7 |
| 7 | 7 |
| 8 | 7 |
| 9 | 7 |
| 10 | 3 |
| 11 | 3 |
| 12 | 3 |
| 13 | 3 |
| 14 | 3 |
| 15 | 10 |
| 16 | 10 |
| 17 | 10 |
| 18 | 10 |
| 19 | 10 |
| 20 | 10 |
| 21 | 10 |
| 22 | 10 |
| 23 | 10 |
| 24 | 10 |
| 25 | 10 |
| 26 | 10 |
| 27 | 10 |
| 28 | 10 |
| 29 | 10 |
| 30 | 10 |
| 31 | 10 |
| 32 | 10 |
| 33 | 10 |
| 34 | 10 |
| 35 | 10 |
| 36 | 10 |
| 37 | 10 |
| 38 | 10 |
| 39 | 8 |
| 40 | 8 |
| 41 | 8 |
| 42 | 8 |
| 43 | 3 |
| 44 | 3 |
| 45 | 3 |
| 46 | 3 |
| 47 | 3 |
| 48 | 3 |
| 49 | 3 |
| 50 | 6 |
| 51 | 6 |
| 52 | 6 |
| 53 | 8 |
| 54 | 8 |
| 55 | 8 |
| 56 | 8 |
| 57 | 8 |
| 58 | 8 |
| 59 | 8 |
| 60 | 8 |
| 61 | 8 |
| 62 | 8 |
| 63 | 5 |
| 64 | 5 |
| 65 | 16 |
| 66 | 16 |
| 67 | 16 |
| 68 | 16 |
| 69 | 16 |
| 70 | 16 |
| 71 | 16 |
| 72 | 16 |
| 73 | 16 |
| 74 | 16 |
| 75 | 16 |
| 76 | 16 |
| 77 | 16 |
| 78 | 16 |
| 79 | 16 |
| 80 | 16 |
| 81 | 16 |
| 82 | 16 |
| 83 | 16 |
| 84 | 16 |
| 85 | 18 |
| 86 | 18 |
| 87 | 18 |
| 88 | 18 |
| 89 | 18 |
| 90 | 18 |
| 91 | 18 |
| 92 | 18 |
| 93 | 18 |
| 94 | 18 |
| 95 | 18 |
| 96 | 18 |
| 97 | 16 |
| 98 | 16 |
| 99 | 16 |
| 100 | 16 |
| 101 | 16 |
| 102 | 12 |
| 103 | 12 |
| 104 | 12 |
| 105 | 8 |
| 106 | 8 |
| 107 | 8 |
| 108 | 8 |
| 109 | 8 |
| 110 | 8 |
| 111 | 8 |
| 112 | 8 |
| 113 | 8 |
| 114 | 8 |
| 115 | 8 |
| 116 | 8 |
| 117 | 8 |
| 118 | 8 |
| 119 | 9 |
| 120 | 9 |
| 121 | 9 |
| 122 | 9 |
| 123 | 9 |
| 124 | 9 |
| 125 | 9 |
| 126 | 9 |
| 127 | 9 |
| 128 | 9 |
| 129 | 9 |
| 130 | 9 |
| 131 | 9 |
| 132 | 9 |
| 133 | 9 |
| 134 | 9 |
| 135 | 9 |
| 136 | 9 |
| 137 | 9 |
| 138 | 9 |
| 139 | 9 |
| 140 | 9 |
| 141 | 9 |
| 142 | 9 |
| 143 | 9 |
| 144 | 9 |
| 145 | 9 |
| 146 | 9 |
| 147 | 9 |
| 148 | 9 |
| 149 | 9 |
| 150 | 9 |
| 151 | 9 |
| 152 | 9 |
| 153 | 9 |
| 154 | 9 |
| 155 | 5 |
| 156 | 5 |
| 157 | 5 |
| 158 | 5 |
| 159 | 2 |
| 160 | 2 |
| 161 | 2 |
| 162 | 2 |
| 163 | 2 |
| 164 | 2 |
| 165 | 2 |
| 166 | 2 |
| 167 | 2 |
| 168 | 2 |
| 169 | 2 |
| 170 | 2 |
| 171 | 2 |
| 172 | 2 |
| 173 | 2 |
| 174 | 2 |
| 175 | 2 |
| 176 | 2 |
| 177 | 0 |
| 178 | 0 |
| 179 | 0 |
| 180 | 0 |
| 181 | 0 |
| 182 | 0 |
| 183 | 0 |
| 184 | 0 |
| 185 | 7 |
| 186 | 7 |
| 187 | 7 |
| 188 | 7 |
| 189 | 7 |
| 190 | 7 |
| 191 | 7 |
| 192 | 7 |
| 193 | 4 |
| 194 | 4 |
| 195 | 4 |
| 196 | 4 |
| 197 | 4 |
| 198 | 4 |
| 199 | 4 |
| 200 | 4 |
| 201 | 4 |
| 202 | 4 |
| 203 | 4 |
| 204 | 4 |
| 205 | 4 |
| 206 | 4 |
| 207 | 4 |
| 208 | 4 |
| 209 | 4 |
| 210 | 4 |
| 211 | 4 |
| 212 | 4 |
| 213 | 4 |
| 214 | 4 |
| 215 | 4 |
| 216 | 4 |
| 217 | 5 |
| 218 | 5 |
| 219 | 5 |
| 220 | 5 |
| 221 | 0 |

# Crew-size scenarios (same activities, norms and calendar)

| Profile | Archetype | Head-count (own direct + indirect) | Subcontract capacity | Working days | Calendar days | Finish | Peak workers | Labour-hours | Resource-limited | Cost (planning only) | Claim |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP-ENT | enterprise | 91 | 12 | 192 | 274 | 2027-12-05 | 27 | 10354.60 | A-STEEL | 1512770.00 | PROVISIONAL - NOT FOR RELIANCE: synthetic test inputs |
| WP-LARGE | large | 48 | 8 | 192 | 274 | 2027-12-05 | 24 | 10354.60 | A-SHORE,A-REBAR,A-STEEL | 1098930.00 | PROVISIONAL - NOT FOR RELIANCE: synthetic test inputs |
| WP-MID | mid | 24 | 6 | 231 | 327 | 2028-01-27 | 18 | 10354.60 | A-EXC,A-EXCH,A-REBAR,A-STEEL,A-PUMP,A-PIPE50,A-ROAD | 754930.00 | PROVISIONAL - NOT FOR RELIANCE: synthetic test inputs |
| WP-SME | sme | 15 | 4 | 422 | 596 | 2028-10-22 | 8 | 10354.60 | A-EXC,A-FORM,A-REBAR,A-STEEL,A-SUPP,A-PUMP,A-PIPE100,A-PIPE50,A-WELD,A-ROAD,A-ELV | 449450.00 | PROVISIONAL - NOT FOR RELIANCE: synthetic test inputs |

# Reading the scenarios

Scenario results compare workforce profiles on the same activities, calendar and norms. They are not an industry benchmark; a doubled workforce does not halve the programme because of dependencies, finite work fronts, shared equipment and rounding of crews.

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Workforce bands are configurable company planning assumptions, not industry-standard categories.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)