# Procurement and long-lead schedule

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D22 |
| Title | Procurement and long-lead schedule |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-PROCUREMENT@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Long-lead items - summary

| Field | Value |
| --- | --- |
| project_id | PRJ-9101 |
| as_of | 2026-10-14 |

# Long-lead items - items

| id | description | package_id | supplier_id | lead_time_weeks | required_on_site | latest_order_date | planned_order_date | actual_order_date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LL-PRJ-9101-001 | Transfer pump skids (SYNTHETIC) |  |  | 20 | 2027-07-15 | 2027-02-25 | 2027-02-21 |  |

# Procurement needs

| ID | Description | Qty | Unit | Reason | Exposure | Priority | Closed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PRC-PRJ-9101-0001 | SYNTHETIC installed baseline: Transfer pump skid supply (long lead) | 2 | nr | Missing rate - no verified price on record |  | Unknown exposure | 1 |
| PRC-PRJ-9101-0002 | SYNTHETIC installed baseline: Stainless steel pipe DN100 supply | 80 | m | Missing rate - no verified price on record |  | Unknown exposure | 1 |
| PRC-PRJ-9101-0003 | SYNTHETIC installed baseline: Pneumatic control valve DN100 supply | 4 | nr | Missing rate - no verified price on record |  | Unknown exposure | 1 |

# RFQ register (drafts are prepared here; nothing is sent by the application)

| RFQ | Package | Supplier | Subject | Status | Response deadline | Issued |
| --- | --- | --- | --- | --- | --- | --- |
| RFQ-PRJ-9101-001 | PKG-PRJ-9101-E |  | Request for Quotation - Dammam Industrial Utilities - Synthetic Tender Closure - Mechanical and HVAC package | Draft |  |  |

# Quotation comparison and levelling - package PKG-PRJ-9101-E (SYNTHETIC suppliers in a demonstration; never live quotations)

Suggested lowest like-for-like quotation: QT-0001 (advisory: a person selects and approves)

| Quotation | Headline total | Approved adjustments | Evaluated total | Validity | Valid until | Coverage | Non-compliant items | Delivery/unloading excluded | Missing items | Like-for-like |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| QT-0001 | 298400.00 | 0 | 298400.00 | Valid | 2026-10-28 | 3/3 | [] | 0 | [] | True |
| QT-0002 | 284800.00 | 21500 | 306300.00 | Valid | 2026-11-04 | 3/3 | [] | 3 | [] | True |
| QT-0003 | 299200.00 | 0 | 299200.00 | Valid | 2026-10-21 | 3/3 | [] | 0 | [] | True |

# Subcontract and package strategy

| Key | package | approach | rationale | Status |
| --- | --- | --- | --- | --- |
| pump | Pump skids (E.08) | Supply-only purchase order with early order date | Long-lead item | Draft |

# Supplier qualification status

| Key | supplier | status | basis | Status |
| --- | --- | --- | --- | --- |
| A | SYNTHETIC Supplier A (fictional) | Not qualified (test) | No qualification evidence supplied | Draft |

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Synthetic quotations are test inputs and never live supplier quotations.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)