## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-D22
Title | Procurement and long-lead schedule
Revision | 2
Issue date | 2027-02-15
Status | Preliminary (DEMONSTRATION)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | T-PROCUREMENT@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Long-lead items - summary
Field | Value
project_id | PRJ-9101
as_of | 2026-10-14

## Long-lead items - items
id | description | package_id | supplier_id | lead_time_weeks | required_on_site | latest_order_date | planned_order_date | actual_order_date
LL-PRJ-9101-001 | Transfer pump skids (SYNTHETIC) |  |  | 20 | 2027-07-15 | 2027-02-25 | 2027-02-21

## Procurement needs
ID | Description | Qty | Unit | Reason | Exposure | Priority | Closed
PRC-PRJ-9101-0001 | SYNTHETIC installed baseline: Transfer pump skid supply (long lead) | 2 | nr | Missing rate - no verified price on record |  | Unknown exposure | 1
PRC-PRJ-9101-0002 | SYNTHETIC installed baseline: Stainless steel pipe DN100 supply | 80 | m | Missing rate - no verified price on record |  | Unknown exposure | 1
PRC-PRJ-9101-0003 | SYNTHETIC installed baseline: Pneumatic control valve DN100 supply | 4 | nr | Missing rate - no verified price on record |  | Unknown exposure | 1

## RFQ register (drafts are pre
RFQ | Package | Supplier | Subject | Status | Response deadline | Issued
RFQ-PRJ-9101-001 | PKG-PRJ-9101-E |  | Request for Quotation - Dammam Industrial Utilities - Synthetic Tender Closure - Mechanical and HVAC package | Draft

## Quotation comparison and lev
Quotation | Headline total | Approved adjustments | Evaluated total | Validity | Valid until | Coverage | Non-compliant items | Delivery/unloading excluded | Missing items | Like-for-like
QT-0001 | 298400.00 | 0 | 298400.00 | Valid | 2026-10-28 | 3/3 | [] | 0 | [] | TRUE
QT-0002 | 284800.00 | 21500 | 306300.00 | Valid | 2026-11-04 | 3/3 | [] | 3 | [] | TRUE
QT-0003 | 299200.00 | 0 | 299200.00 | Valid | 2026-10-21 | 3/3 | [] | 0 | [] | TRUE

## Subcontract and package stra
Key | package | approach | rationale | Status
pump | Pump skids (E.08) | Supply-only purchase order with early order date | Long-lead item | Draft

## Supplier qualification statu
Key | supplier | status | basis | Status
A | SYNTHETIC Supplier A (fictional) | Not qualified (test) | No qualification evidence supplied | Draft