## Document
SYNTHETIC / DEMONSTRATION MARKINGS AND STATUS
DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER ¦ approvals by: test principals in environment 'test'
Project ID | PRJ-9101
Project name | Dammam Industrial Utilities - Synthetic Tender Closure
Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER)
Document ID | PRJ-9101-D35
Title | Estimate audit and reconciliation report
Revision | 2
Issue date | 2027-02-15
Status | Preliminary (DEMONSTRATION)
Author | test-estimator
Reviewer | not yet reviewed
Estimate version | v2
Estimate fingerprint | 48d0f9242dc910b7
Template | T-RECON@1.0.0
Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data

## Gate
Item | Result
Final gate blocked | False
Blockers | 0
Replay of frozen version reproduces totals | True
Replay differences | none

## Findings
Rule | Severity | Entity | Message | Status
PLANT_HIRE_DAYS | High | SYN-C-050 | Plant billable days differ from the programme hire window | Accepted Exception
SYNTHETIC_DEMO | Low | PRJ-9101 | Synthetic demonstration data present | Open
POSSIBLE_DUPLICATE_ITEM | Medium | C-071 | Possible duplicate BOQ item / cost in several packages | Open
UNAPPROVED_ADOPTED_ASSUMPTION | Medium | PRJ-9101 | Adopted assumption not approved | Open

## Accepted exceptions
Rule | Entity | By | Role | Actor type | Environment
PLANT_HIRE_DAYS | SYN-C-050 | test-commercial | Commercial Approver | test | test