# Productivity and programme assumptions report

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D37 |
| Title | Productivity and programme assumptions report |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-PRODUCTIVITY@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Productivity norms used

| Norm | Ver | Trade | Activity | Basis | Value | Unit | Status | Evidence | Origin | Source | Flag |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N-BACK | 1 | Civil | Backfill and compaction | crew_output_per_crew_day | 80 | m3 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-CABLE | 1 | Electrical | Cable pulling | crew_output_per_crew_day | 120 | m | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-COAT | 1 | Piping | Coating | crew_output_per_crew_day | 60 | m2 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-EXC | 1 | Civil | Trench excavation | crew_output_per_crew_day | 60 | m3 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-EXCH | 1 | Civil | Excavation in hard material | crew_output_per_crew_day | 12 | m3 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-FIBRE | 1 | ELV | Fibre backbone | crew_output_per_crew_day | 100 | m | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-FORM | 1 | Structural | Formwork | crew_output_per_crew_day | 20 | m2 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-NDT | 1 | Piping | Radiographic testing | crew_output_per_crew_day | 6 | joint | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-PIPE | 1 | Piping | Pipe fabrication and installation | labour_hours_per_unit | 0.5 | inch_dia | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-POUR | 1 | Structural | Concrete pour | crew_output_per_crew_day | 24 | m3 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-PUMP | 1 | Mechanical | Pump skid setting | crew_output_per_crew_day | 0.5 | nr | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-REBAR | 1 | Structural | Reinforcement fix | labour_hours_per_unit | 0.04 | kg | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-ROAD | 1 | Civil | Road reinstatement | crew_output_per_crew_day | 45 | m2 | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-SHORE | 1 | Civil | Trench shoring | crew_output_per_crew_day | 40 | m | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-STEEL | 1 | Structural | Steel erection | crew_output_per_crew_day | 2500 | kg | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-SUPP | 1 | Piping | Support fabrication | crew_output_per_crew_day | 500 | kg | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-TRAY | 1 | Electrical | Cable tray | crew_output_per_crew_day | 45 | m | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |
| N-WELD | 1 | Piping | Butt welding | labour_hours_per_unit | 3 | joint | Approved | synthetic | synthetic | SYNTHETIC TEST DATA - NOT AN INDUSTRY BENCHMARK - NOT A MARKET QUOTE | synthetic |

# Gaps

| Activity | Kind | Detail |
| --- | --- | --- |
| A-EXC | NORM_EVIDENCE_SYNTHETIC | norm N-EXC v1: evidence 'synthetic' |
| A-EXCH | NORM_EVIDENCE_SYNTHETIC | norm N-EXCH v1: evidence 'synthetic' |
| A-SHORE | NORM_EVIDENCE_SYNTHETIC | norm N-SHORE v1: evidence 'synthetic' |
| A-FORM | NORM_EVIDENCE_SYNTHETIC | norm N-FORM v1: evidence 'synthetic' |
| A-REBAR | NORM_EVIDENCE_SYNTHETIC | norm N-REBAR v1: evidence 'synthetic' |
| A-POUR | NORM_EVIDENCE_SYNTHETIC | norm N-POUR v1: evidence 'synthetic' |
| A-STEEL | NORM_EVIDENCE_SYNTHETIC | norm N-STEEL v1: evidence 'synthetic' |
| A-SUPP | NORM_EVIDENCE_SYNTHETIC | norm N-SUPP v1: evidence 'synthetic' |
| A-PUMP | NORM_EVIDENCE_SYNTHETIC | norm N-PUMP v1: evidence 'synthetic' |
| A-PIPE100 | NORM_EVIDENCE_SYNTHETIC | norm N-PIPE v1: evidence 'synthetic' |
| A-PIPE50 | NORM_EVIDENCE_SYNTHETIC | norm N-PIPE v1: evidence 'synthetic' |
| A-WELD | NORM_EVIDENCE_SYNTHETIC | norm N-WELD v1: evidence 'synthetic' |
| A-NDT | NORM_EVIDENCE_SYNTHETIC | norm N-NDT v1: evidence 'synthetic' |
| A-BACK | NORM_EVIDENCE_SYNTHETIC | norm N-BACK v1: evidence 'synthetic' |
| A-ROAD | NORM_EVIDENCE_SYNTHETIC | norm N-ROAD v1: evidence 'synthetic' |
| A-COAT | NORM_EVIDENCE_SYNTHETIC | norm N-COAT v1: evidence 'synthetic' |
| A-TRAY | NORM_EVIDENCE_SYNTHETIC | norm N-TRAY v1: evidence 'synthetic' |
| A-CABLE | NORM_EVIDENCE_SYNTHETIC | norm N-CABLE v1: evidence 'synthetic' |
| A-ELV | NORM_EVIDENCE_SYNTHETIC | norm N-FIBRE v1: evidence 'synthetic' |

# Method

Required labour-hours = quantity x approved labour-hours per unit; crew-days = hours / (productive hours per worker x crew size); duration = ceil(crew-days / effective crews). Crew-output norms use units per crew-day and do not re-apply the labour-hours formula.

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

No norm is an industry benchmark; every value is a sourced company/project entry.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)