# Estimate risk / sensitivity report

DEMONSTRATION EXPORT - NOT SUBMISSION READY - NOT APPROVED FOR ANY REAL TENDER | approvals by: test principals in environment 'test'

SYNTHETIC TEST DATA - FICTIONAL CUSTOMER - NOT A REAL TENDER - NOT A MARKET QUOTE - NOT FOR SUBMISSION

| Project ID | PRJ-9101 |
| --- | --- |
| Project name | Dammam Industrial Utilities - Synthetic Tender Closure |
| Customer | Gulf Process Utilities Co. (FICTIONAL SYNTHETIC CUSTOMER) |
| Document ID | PRJ-9101-D40 |
| Title | Estimate risk / sensitivity report |
| Revision | 2 |
| Issue date | 2027-02-15 |
| Status | Preliminary (DEMONSTRATION) |
| Author | test-estimator |
| Reviewer | not yet reviewed |
| Estimate version | v2 |
| Estimate fingerprint | 48d0f9242dc910b7 |
| Template | T-SENSITIVITY@1.0.0 |
| Confidentiality | CONFIDENTIAL (synthetic test data) - no real customer or supplier data |

# Quantified risk - summary

| Field | Value |
| --- | --- |
| project_id | PRJ-9101 |
| method | Independent risks: Bernoulli(p) x triangular(low, likely, high); range items: triangular deviation from the value in the estimate. No correlation; schedule impacts summed (no critical-path logic). |
| inputs | {"risks": [{"id": "RSK-PRJ-9101-001", "title": "Ground conditions in hard material", "p_pct": "30.0", "low": "20000", "likely": "60000", "high": "150000", "days": "0"}, {"id": "RSK-PRJ-9101-002", "title": "Pump skid delivery delay", "p_pct": "25.00", "low": "0", "likely": "45000", "high": "120000... |
| expected_value | {"per_risk": {"RSK-PRJ-9101-001": "23000.00000000000000000000000", "RSK-PRJ-9101-002": "13750.00", "RSK-PRJ-9101-003": "8666.666666666666666666666666"}, "per_range": {}, "total": "45416.66666666666666666666667"} |
| simulation | {"trials": 10000, "seed": 20260101, "mean": "45800.142692242596", "std_dev": "50674.55977888334", "min": "0.0", "max": "273065.26326442213", "percentiles": {"P10": "0.0", "P50": "36203.37348367494", "P80": "87722.9083654505", "P90": "118203.94229669428"}, "schedule_days": null, "histogram": [{"fr... |
| target | P80 |
| proposed_provision | 87722.9083654505 |
| policy_provision | 149798.16 |
| difference_vs_policy | -62075.2516345495 |
| note | PROPOSAL ONLY: the simulation suggests a provision of 87,722.91 at P80. The contingency and risk amounts in the commercial policy are decided and approved by people. |
| estimate_state | Complete |

# Escalation - summary

| Field | Value |
| --- | --- |
| project_id | PRJ-9101 |
| escalation_total | 76678.65 |
| scheduled_base_total | 3452410.00 |
| direct_cost_total | 3452410.00 |
| complete | True |
| status | COMPLETE for the cost within profile scope |
| unescalated_eligible_cost | 0.00 |
| outside_profile_scope_cost | 0.00 |
| not_covered_by_any_profile | 0.00 |
| policy_escalation | 0.00 |
| note | Escalation is compounded from each profile's base date to mid-month of each programme month. Cost not tied to a task by cost-code/WBS scope is NOT escalated and is listed. Index values (if shown) are information; the percentages are the company's decision. |
| estimate_state | Complete |

# Escalation - profiles

| profile | name | annual_pct | base_date | basis | scope_kind | scope_cost_prefix | periods | base_total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ESC-35 | SYNTHETIC annual escalation | 3.50 | 2027-01-01 | SYNTHETIC test assumption | all |  | [{"period": "2027-03", "mid": "2027-03-15", "base_amount": "189409.23", "factor": "1.01", "escalated": "190753.37", "escalation": "1344.14"}, {"period": "2027-04", "mid": "2027-04-15", "base_amount": "127873.85", "factor": "1.01", "escalated": "129151.02", "escalation": "1277.17"}, {"period": "20... | 3452410.00 |

# Assumptions, exclusions and limitations

Quantities are human-measured BOQ quantities; the application does not measure drawings.

Figures are taken from frozen estimate version v2 (fingerprint 48d0f9242dc910b7).

SYNTHETIC / DEMONSTRATION data: rates, quotations, productivity norms, customer and responses are fictional test inputs, not market evidence.

Sensitivity uses only quantified ranges that a person entered and approved.

# Source references

Frozen estimate version v2 (fingerprint 48d0f9242dc910b7), totals and pricing schedule

Registers in the application database (see document D33 for received documents, D08 for assumptions, D25 for queries)